## Guidance
Guidance for completing this plan
This planning tool is a simple tool to complete a project plan, if you want to use your own plan, please do so.
1 | Check out the example tabs
2 | Complete the planning sheet questions, you don't need to go overboard on detail
3 | Complete the gantt template by adding the tasks and shading the appropriate cells
4 | Use the plan for your project

## Planning sheet
Planning
Purpose
How the funding will help
Timescales
Key milestones and deliverables

## Gantt template
Kent Waste Prevention Fund Gantt Template
| 2026 |  |  |  | 2027
| September | October | November | December | January | February | March | April | May | June | July | August | September
Planning
Implementation

## Example planning sheet
Example Planning
EXAMPLE Purpose: | EXAMPLE This project is designed to help reduce textiles waste across Kent by collecting materials that would otherwise have gone to waste by collecting them for use in quilts and art projects
EXAMPLE How will funding help: | EXAMPLE We will use the funding to create collection points for waste textiles (such as scrap fabric, and items not suitable for reuse by charity shops), as well as organising teaching events to show people how to make decorative quilts. Funding will also be used to purchase second-hand sewing machines and needles/thread/etc.
EXAMPLE Timescales: | EXAMPLE We aim to start collecting fabric from April 2025, and will hold a workshop every three months for a year. We will also create online worksheets to teach people who to make quilts outside of the workshops, so that they can use their own scrap fabric.
EXAMPLE Key milestones and Deliverables | EXAMPLE April 2025: program launch, textiles collection begins
June 2025: first in-person event
September 2025: second in-person event
December 2025: third in-person event & Christmas gathering
March 2026: fourth in-person event
May 2026: final report to Kent County Council

## Example gantt template
Example Kent Waste Prevention Fund Planning Template
| 2026 |  |  |  | 2027
| September | October | November | December | January | February | March | April | May | June | July | August | September
Planning
EXAMPLE Fill in Risk Assessment
EXAMPLE Book venues
EXAMPLE Hire equipment
Implementation
EXAMPLE On the day set up
EXAMPLE Transport
EXAMPLE Volunteers
EXAMPLE Reporting