e-Waste Warriors – Swale cluster planner

Schools:

Fulston Manor

Grove Park Primary School

South Avenue Primary School

Ethelbert Road Primary School

The Sittingbourne School

Bobbing Village School

Iwade Primary School

| Activity | Date | Location/delivery |
| --- | --- | --- |
| Induction webinar | 15/12/25 | Online – Teams |
| School to receive comms pack | w/c 15/12/25 | Email |
| School to send out comms email to parents and put up posters around school | w/c 05/01/26 | Email |
| In-person meeting KCC and school (project lead and person responsible for bins) | Thursday 15/01/26 or Friday 16/01/26 | In-person in schools |
| School to receive Team Repair kits and recycling bins | Kits w/c 12/01/26 Bins w/c 12/01/26 | Sent to school |
| Assembly | Thursday 15/01/26 or Friday 16/01/26 | In schools for primary schools. Youtube video to secondary schools |
| Launch of recycling/repair bins to parents/students | 19/01/26 | In schools |
| Team Repair lessons/sessions Retro Games Console Resource Pack (V2) | w/c 19/01/26or following week | In schools |
| Collection of recycled WEEE | Friday 13/02/26 Potentially an ad-hoc collection if bins fill up | In schools |
| Schools to send repair event email to parents | tbc | Email |
| Return Team Repair kits | As soon as completed – liaise with Team Repair | In schools |
| Repair event | tbc |  |
| End of collections and lock bins | 13/02/26 | In schools |
| Secure storage of bins until collection | 13/02/26 until advised by KCC | In schools |
| Schools to be informed of recycling tonnage and no. of items repaired | February/March 2026 | Email |
| Follow-up thoughts | Survey to follow completion | Email |
| Full competition prize giving | April 2026 | TBC |

Contact:

Richard Izzard – Project Manager 03000 411531 Richard.izzard@kent.gov.uk